## 00_Program_Setup
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Program Setup | Create master folder tree | /docs, /ops, /legal, /marketing, /design, /analytics, /sop, /packaging | PM | Drive/Notion | High |  |  | Use naming YYYYMMDD_prefix
Program Setup | Baseline timeline & sprints | 4 sprints (W1–W4) + backlog | PM | Gantt/Monday | High
Program Setup | Roles & RACI approval | Marketing, Ops, CX, Tech, Finance | CEO | Doc | High |  |  | Map to sheets
Program Setup | Connect domains & email sending | SPF/DKIM/DMARC for hairoticmen.de | Tech | cPanel + WP Mail SMTP | High |  |  | Fix SMTP timeout issue

## 01_Legal_Compliance
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Legal | Impressum (DE) | Company, address, USt-IdNr., contact | Legal | WP Page | High
Legal | AGB (Terms) | Return, warranty, payment, shipping, liability | Legal | WP Page | High
Legal | Widerrufsrecht (14 Tage) | Model withdrawal form + instructions | Legal | WP Page | High
Legal | Datenschutzerklärung (GDPR/DSGVO) | Cookies, analytics, CRM, newsletter | Legal | WP Page | High
Legal | Cookie Banner & CMP | Consent for pixels & tracking | Tech/Legal | CookieYes/Complianz | High
Legal | Kosmetik-VO EU 1223/2009 | INCI, CPNP, safety file reference | QA/Legal | Docs | High |  |  | Link each SKU dossier
Legal | VerpackG (LUCID) Registration | Packaging quantities & system | Ops/Legal | LUCID | High

## 02_Storefront
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Storefront | Theme & Brand setup | Black/White/Gold palette, logo placements | Design | WP + Elementor | High |  |  | Follow brand guide
Storefront | Product PDP template | Gallery+Video, Benefits, How‑to, INCI, Reviews, Points | Marketing | WooCommerce | High
Storefront | Catalog & attributes | Sizes, scents, bundles | Ops | WooCommerce | High
Storefront | Payments | PayPal, Klarna, WooCommerce Payments | Tech/Finance | WC Payments | High
Storefront | Shipping table | DE free ≥49.99€, EU free ≥99.99€ | Ops | Flexible Shipping/DHL | High
Storefront | Taxes & VAT | 19% VAT incl., invoice template | Finance | Woo + Invoicing | High

## 03_Marketing_Ads
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Marketing | Meta Business setup | BM, Ad accounts, Pixels | Marketing | Meta | High
Marketing | Google Merchant Center + PMAX | Feed from Woo, policies | Marketing | Google | High
Marketing | TikTok Pixel | Optional v2 | Marketing | TikTok | Medium
Marketing | Campaign structure | C1 Prospecting, C2 Engagement, C3 Retargeting | Marketing | Meta/Google | High
Marketing | Creative pack v1 | 5 Reels, 10 images, UGC | Design | Canva/Studio | High
Marketing | Copy bank (DE) | Hooks, CTAs, compliance | Marketing | Doc | High

## 04_Content_Email
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Content | Email Flows (DE) import | 5 flows uploaded (DOCX delivered) | Marketing | MailPoet/WC | High |  |  | File link below | sandbox:/mnt/data/HAIROTICMEN_Email_Flows_Template_DE_2025-10-04.docx
Content | FAQ page | Versand, Rückgabe, Anwendung, Allergie, Kontakt | Marketing | WP Page | High
Content | Tutorials page | How‑to videos per SKU | Marketing | WP Page | Medium
Content | Blog plan | 4 SEO articles (launch) | Marketing | WP | Medium

## 05_Loyalty
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Loyalty | Point rules | Signup +20, First order +50, 1€/1pt, Review +10, Refer +25 | Marketing | myCred | High
Loyalty | Tiers | Silver/Gold/Diamond multipliers | Marketing | myCred | Medium
Loyalty | Hooks config | order_completed, comment_approved, referral | Tech | myCred | High
Loyalty | Notification texts (DE) | Templates for award/spend | Marketing | NotificationX | High

## 06_Operations_SOP
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Operations | Order processing SOP | Import → Pick → Pack → Label → Handover | Ops Lead | SOP Doc | High
Operations | QC checklist | Seals, batch/expiry, damage check | QA | SOP Doc | High
Operations | Refund & RMA SOP | RMA tickets, labels, inspection, refund <=5d | CX/Finance | SOP Doc | High
Operations | Inventory & Reorder | Safety stock, cycle count monthly | Ops | Sheet | High

## 07_Logistics_DHL
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Logistics | DHL for WooCommerce setup | Credentials, product weights, label print | Ops/Tech | DHL Plugin | High
Logistics | TrackShip integration | Auto tracking emails & status updates | Ops/Tech | TrackShip | High
Logistics | Return labels process | On request via portal/email | CX/Ops | DHL Returns | High
Logistics | Shipping materials | Box sizes, fillers, tape, label sleeves | Ops | Pack list | High

## 08_CX_Support
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
CX | Hairo Assistant scripts (DE) | Pre‑purchase, tracking, returns, product fit | CX Lead | Chatbot | High
CX | Contact channels | Live chat, Email, WhatsApp, IG DM | CX | WP/Integrations | High
CX | SLA policy | ≤2h (10–18 CET), ≤24h off‑hours | CX | Policy | High
CX | Macros (DE) | Shipping, returns, recommendation, apology | CX | Helpdesk | High

## 09_Analytics
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Analytics | GA4 + GTM + Pixels | Events: view_item, add_to_cart, purchase | Tech | GA4/GTM | High
Analytics | UTM taxonomy | utm_source/medium/campaign/content | Marketing | Doc | High
Analytics | Dashboards | Weekly KPIs: CR, AOV, ROAS, CAC, LTV | Marketing | Looker/Data Studio | Medium
Analytics | A/B testing plan | PDP & checkout experiments | Marketing | Tool | Medium

## 10_Risk_Escalation
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Risk | Shipping delays playbook | Proactive email + 10% coupon + goodwill points | CX/Marketing | Doc | High
Risk | Stockout plan | Waitlist + restock email | Ops/Marketing | Doc | High
Risk | Negative reviews protocol | Reply ≤24h + solution + loyalty gesture | CX | Doc | High
Risk | QC incident response | Stop‑ship lot, RCA, replace/recall | QA/Ops | Doc | High

## 11_Packaging
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Packaging | Box size matrix | All SKUs → outer boxes (XS–XL, KIT 3 sizes) | Ops/Design | Sheet | High |  |  | Use user's docs sizes
Packaging | Labeling spec | Front/Back layout, INCI, barcode (EAN) | Design/QA | AI file + PDF | High
Packaging | Sustainability note | Recycling marks, VerpackG compliance | Legal/Design | Doc | Medium
Packaging | Packing SOP | Void fill, invoice insert, return instructions | Ops | SOP Doc | High

## 12_Documents_Index
Workstream | Task | Details/Acceptance Criteria | Owner | Tool/System | Priority | Due Date | Status | Notes | Link/File
Doc Index | AGB (DE) | Legal terms for store | Legal | Doc | High
Doc Index | Widerrufsrecht (DE) | Return policy + form | Legal | Doc | High
Doc Index | Datenschutz (DE) | GDPR/DSGVO | Legal | Doc | High
Doc Index | Impressum (DE) | Company legal info | Legal | WP Page | High
Doc Index | SOP – Order Processing | Ops manual | Ops | Doc | High
Doc Index | SOP – Returns (RMA) | CX/Ops manual | CX/Ops | Doc | High
Doc Index | QC Checklist | QA sheet | QA | Sheet | High
Doc Index | DHL Integration Guide | Woo + TrackShip steps | Tech/Ops | Doc | High
Doc Index | myCred Hooks & Templates (DE) | Rules + Log messages | Tech/Marketing | Doc | High
Doc Index | NotificationX Templates (DE) | On‑site popups & social proof | Marketing | Doc | High
Doc Index | Packaging Matrix & Specs | All box sizes & labels | Ops/Design | Sheet | High